## Costs
Category | Item | Estimated Cost | Actual Cost | Date | Notes
Labour | Backend development | 24000 | 27600 | 2026-03-31 | Two extra sprints for API changes
Labour | Frontend development | 18000 | 18900 | 2026-03-31
Labour | QA and testing | 8000 | 7400 | 2026-04-15 | Automated suite reused
Labour | Project management | 9000 | 9300 | 2026-04-30
Labour | UX design | 6500 | 6200 | 2026-02-28
Software | Cloud hosting (annual) | 4800 | 5150 | 2026-01-31 | Region price change
Software | CI/CD licences | 1200 | 1200 | 2026-01-31
Software | Monitoring SaaS | 900 | 2950 | 2026-02-15 | Upgraded tier after incident
Software | Database licence | 3500 | 3500 | 2026-01-31
Hardware | Developer laptops | 7500 | 7350 | 2026-01-20
Hardware | Test devices | 1500 | 1380 | 2026-01-20
Training | Security awareness course | 1200 | 1000 | 2026-02-10
Training | Cloud certification | 2000 | 2400 | 2026-03-05
Consulting | Penetration test | 6000 | 6000 | 2026-04-20
Consulting | Accessibility audit | 2500 | 2750 | 2026-04-25
Travel | Client workshops | 3000 | 4900 | 2026-03-12 | Extra on-site visit
Contingency | Emergency data recovery | 0 | 3800 | 2026-03-20 | Unplanned: disk failure on staging
Other | Office supplies | 400 | 420 | 2026-02-01